Directive No 13

(issued pursuant to section 7 of the Public Procurement Act)

KPIs for Procurement Lead Time

- For the purpose of this Directive, procurement lead time is defined as the interval in calendar days between the preparation of bidding documents and the issue of award of contract. The time taken for challenge and appeal procedures has been excluded.  An appropriate procurement lead time, inter-alia, takes into account the bid submission period allowing sufficient time for bidders to prepare and submit their bids and reasonable time for examination, evaluation, approval and award of contracts.

- Public bodies should aim at attaining the following lead times for procurements using Open Advertised Bidding.

| Types of contracts | Procurement Lead Time for Major contracts (days) | Procurement Lead Time for Non-major contracts (days) |
| --- | --- | --- |
| Works (without prequalification) | 120 | 90 |
| Goods (except pharmaceuticals) | 100 | 75 |
| Other Services | 95 | 70 |
| Pharmaceuticals | 110 | 85 |

- An indicative time frame for the different stages of the bidding process is at annex.

4. The procurement lead time for various contracts awarded by public bodies will be closely monitored by this Office. Public bodies are required to submit a brief report when submitting their respective return of procurement activities for those procurements which have exceeded the set lead time.

5. This Directive takes effect as from 03 June 2013.

Procurement Policy Office

29 May 2013

ANNEX

Proposed time to improve the various stages of the bidding process

| Stages of the Procurement Process | Type of Contracts | Actual Time (2012) | Proposed Time |
| --- | --- | --- | --- |
| 1.1 Preparation of bidding documents | Works Roads Sewerage Other works Goods Services Pharmaceuticals | 28 days 21 days 5 days | 21 days 14 days 5 days |
| 1.2 Vetting of bidding documents (by CPB) | Works Roads Sewerage Other works Goods Services Pharmaceuticals | 30 days 29 days 38 days 28 days 13 days 15 days | 15 days 10 days 10 days |
| 1.3 Rectification of bidding documents by Public bodies prior to launching | Works Roads Sewerage Other works Goods Services Pharmaceuticals | 36 days 62 days 45 days 38 days 30 days 19 days | 15 days 15 days 15 days |
| 1.4 Bid submission Time | Works Roads Sewerage Other works Goods Services Pharmaceuticals | 42 days 30 days 35 days | 35 days 30 days 30 days |
| 1.5 Bid Evaluation | Works Roads Sewerage Other works Goods Services Pharmaceuticals | 16 days 48 days 33 days 54 days 25 days | 21 days 21 days 15 days 35 days |
| 1.6 Recommendation to award by CPB | Works Roads Sewerage Other works Goods Services Pharmaceuticals | 19 days 7 days 24 days 14 days 20 days ----------- | 7 days 7 days 10 days |
| 1.7 Award (issue of notification) | All contracts | Average of 25 days (w/o Challenge and Review) | 5 days |
| 1.8 Prequalification/ Shortlisting of suppliers/ consulting firms | Works Goods Consultancy (EOI) | 84 days 70 days 42 days | 77 days 63 days 35 days |